## Info
ASUMPTIONS AND DEPENDENCIES
Files listed below are only used during this implementation release. Any addition of the files will change the timeline.
LOA issue in current empyrean file which will be fixed later. Rebika to confirm/inform.
This implementation will go through scrub engine
Request Received for Implementation on 2016/12/05
Latest File received Date: 2016/12/01
Initial set of eligibility file/s
traffk/20161025/Ethos/empyrean/
EthosEnergy_ELIG_10202016.txt
Request Received for Implementation on 2016/10/27
File received Date: 2016/10/28
Fiest set of pharmacy file/s
traffk/20161027/Ethos/express-scripts/
EthosEnergy_CDL6848_20161026.081046.txt
traffk/20161019/Ethos/empyrean/
EthosEnergy_ELIG_10062016.txt
EthosEnergy_ELIG_10132016.txt
traffk/20161025/Ethos/empyrean/
EthosEnergy_ELIG_10202016.txt
traffk/20161101/Ethos/empyrean/
EthosEnergy_ELIG_10272016.txt
traffk/20161103/Ethos/empyrean/
EthosEnergy_ELIG_11032016.txt
traffk/20161111/Ethos/empyrean/
EthosEnergy_ELIG_11102016.txt
traffk/20161117/Ethos/empyrean/
EthosEnergy_ELIG_11172016.txt
traffk/20161123/Ethos/empyrean/ [Test File Not included]
TraffkExport-TST-11-16.txt
traffk/20161130/Ethos/empyrean/
EthosEnergy_ELIG_11242016.txt
traffk/20161201/Ethos/empyrean/
EthosEnergy_ELIG_12012016.txt
Known Issue/s
LOA fields missing in currentl empyrean files and will be fixed later. Rebiika to update on this.

## Elig_Timeline
Timeline for Traffk - Ethos - Benefits Eligibility file Implementation Details scope of this release is available at: https://svn.deerwalk.com/versions/2655
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import, Layout verification and analysis | 2016-12-05 | 1 | 2016-12-05 | Subhad | Completed
| DSD preparation (Eligbilility) | 2016-12-06 | 1 | 2016-12-06 | Subhad | Completed | Update/s if any
| DA Checklist preparation | 2016-12-06 | 1 | 2016-12-06 | Subhad | Completed
| DSD and DA Checklist Review and Sign-off | 2016-12-07 | 1 | 2016-12-07 | Rebika/subhad | Completed
SPT
| DSD Implementation (Eligbilility) | 2016-12-08 | 2 | 2016-12-09 | Binod/Rajesh | Completed
| Scrub Engine Configuration | 2016-12-12 | 1 | 2016-12-12 | Binod/Rajesh | Completed
| Unit Testing | 2016-12-13 | 1 | 2016-12-13 | Binod/Rajesh | Completed
QA
| Test Data Preparation (Eligbilility) | 2016-12-08 | 1 | 2016-12-08 | Shishir/Akesh | Completed
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-12-13 | 1 | 2016-12-13 | Nisha/Processing/Surya | Completed
| Scrubbing | 2016-12-14 | 1 | 2016-12-14 | Processing | Completed |  | 2016-01-12
| Scrub QC and Sign-off | 2016-12-15 | 2 | 2016-12-16 | Shishir/Akesh | Completed |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-12-21 | 1 | 2016-12-21 | Subhad/Binod | Ongoing | Delayed until we received feedback on open issues from client
| Re- scrub | 2016-12-22 | 1 | 2016-12-22 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-12-23 | 1 | 2016-12-23 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2016-12-26 | 1 | 2016-12-26 | Subhad/Binod | Not Started
| Re- scrub | 2016-12-27 | 1 | 2016-12-27 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-12-28 | 1 | 2016-12-28 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2016-12-29 | 1 | 2016-12-29 | Subhad/Binod | Not Started | If any
| Re- scrub | 2016-12-29 | 1 | 2016-12-29 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2016-12-30 | 1 | 2016-12-30 | Shishir/Akesh | Not Started | If any
| App Processing | 2017-01-02 | 1 | 2017-01-02 | Processing | Not Started |  | 2016-01-14
| App QC | 2017-01-03 | 1 | 2017-01-03 | Raghu | Not Started |  | 2016-01-14
| Issue fixes for App | 2017-01-04 | 1 | 2017-01-04 | Subhad/Binod/Abhinayak | Not Started | If any
| Re-App Processing | 2017-01-04 | 1 | 2017-01-04 | Processing | Not Started | If any
| App QC | 2017-01-05 | 1 | 2017-01-05 | Raghu | Not Started | If any
| Production Release | 2017-01-06 | 1 | 2017-01-06 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Estimation_AntivImplementat (2 (hidden)
Revised Timeline for Avintiv Implementation Details scope of this release is available at: https://svn.deerwalk.com/projects/usi/roadmap
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import and Analysis - Eligibility and Pharmacy | 2016-08-01 | 1 | 2016-08-01 | Subhad/Sudeep | Not Started
| DSD preparation - Eligibility and Pharmacy | 2016-08-02 | 2 | 2016-08-03 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Eligibility and Pharmacy | 2016-08-04 | 2 | 2016-08-05 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Eligibility and Pharmacy | 2016-08-06 | 1 | 2016-08-06 | Rebika | Not Started
| File Import and Analysis - Medical | 2016-08-09 | 1 | 2016-08-09 | Subhad/Sudeep | Not Started
| DSD preparation - Medical | 2016-08-10 | 2 | 2016-01-01 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Medical | 2016-08-12 | 1 | 2016-08-12 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Medical | 2016-08-15 | 1 | 2016-08-15 | Rebika | Not Started
SPT
| DSD Implementation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 6 | 2016-08-08 | Binod/Rasa | Not Started
| Scrub Engine Configuration |  | 1
| Unit Testing | 2016-08-09 | 2 | 2016-08-10 | Binod/Rasa | Not Started
QA
| Test Data Preparation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 4 | 2016-08-04 | Surya | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-08-11 | 1 | 2016-08-11 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2016-08-12 | 1 | 2016-08-12 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2016-08-15 | 3 | 2016-08-17 | Surya | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-08-17 | 2 | 2016-08-18 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-19 | 1 | 2016-08-19 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-22 | 2 | 2016-08-23 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started | If any
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started | If any
| App Processing | 2016-08-26 | 1 | 2016-08-26 | Processing | Not Started |  | 2016-01-14
| App QC | 2016-08-29 | 1 | 2016-08-29 | Raghu | Not Started |  | 2016-01-14
| Production Release | 2016-08-30 | 1 | 2016-08-30 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Elig_&_Rx_Timeline (hidden)
Timeline for Traffk - Ethos - Benefits Eligibility and Rx files Implementation Details scope of this release is available at: https://svn.deerwalk.com/versions/2655
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
FOR ELIGIBILITY
DA
| File Import, Layout verification and analysis | 2016-10-24 | 2 | 2016-10-26 | Subhad/Diya | Completed
| DSD preparation | 2016-10-27 | 1 | 2016-10-27 | Subhad/Diya | Ongoing
| DA Checklist preparation | 2016-10-28 | 1 | 2016-10-28 | Subhad/Diya | Ongoing
| DSD and DA Checklist Review and Sign-off | 2016-11-02 | 1 | 2016-11-02 | Rebika | Not Started
SPT
| DSD Implementation | 2016-11-03 | 2 | 2016-11-04 | Binod/Rajesh | Not Started
| Scrub Engine Configuration | 2016-11-07 | 1 | 2016-11-07 | Binod/Rajesh | Not Started
| Unit Testing | 2016-11-08 | 2 | 2016-11-08 | Binod/Rajesh | Not Started
QA
| Test Data Preparation | 2016-11-03 | 1 | 2016-11-03 | Shishir/Akesh | Not Started
FOR PHARMACY
DA
| File Import, Layout verification and analysis | 2016-10-28 | 2 | 2016-10-31 | Subhad/Diya | Completed
| DSD preparation | 2016-11-02 | 1 | 2016-11-02 | Subhad/Diya | Ongoing
| DA Checklist preparation | 2016-11-03 | 1 | 2016-11-03 | Subhad/Diya | Ongoing
| DSD and DA Checklist Review and Sign-off | 2016-11-04 | 1 | 2016-11-04 | Rebika | Not Started
SPT
| DSD Implementation | 2016-11-07 | 2 | 2016-11-08 | Binod/Rajesh | Not Started
| Scrub Engine Configuration | 2016-11-09 | 1 | 2016-11-09 | Binod/Rajesh | Not Started
| Unit Testing | 2016-11-10 | 2 | 2016-11-11 | Binod/Rajesh | Not Started
QA
| Test Data Preparation | 2016-11-07 | 1 | 2016-11-07 | Shishir/Akesh | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-11-11 | 1 | 2016-11-11 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2016-11-14 | 1 | 2016-11-14 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2016-11-15 | 3 | 2016-11-17 | Shishir/Akesh | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-11-18 | 2 | 2016-11-21 | Subhad/Binod | Not Started
| Re- scrub | 2016-11-21 | 1 | 2016-11-21 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-11-22 | 2 | 2016-11-23 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2016-11-23 | 1 | 2016-11-23 | Subhad/Binod | Not Started
| Re- scrub | 2016-11-24 | 1 | 2016-11-24 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-11-25 | 1 | 2016-11-25 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2016-11-28 | 1 | 2016-11-28 | Subhad/Binod | Not Started | If any
| Re- scrub | 2016-11-29 | 1 | 2016-11-29 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2016-11-30 | 1 | 2016-11-30 | Shishir/Akesh | Not Started | If any
| App Processing | 2016-12-01 | 1 | 2016-12-01 | Processing | Not Started |  | 2016-01-14
| App QC | 2016-12-02 | 1 | 2016-12-02 | Raghu | Not Started |  | 2016-01-14
| Production Release | 2016-12-05 | 1 | 2016-12-05 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Holidays
Holidays