## Info
ASUMPTIONS AND DEPENDENCIES
Files listed below are only used during this implementation release. Any addition of the files will change the timeline.
No Account structure/s are considered as we do not have any update till date.
This implementation will go through scrub engine
Request Received for Implementation on 2016/12/5
File received Date: 2016/11/30
Fiest set of pharmacy file/s
traffk/20161130/Ethos/express-scripts/
EthosEnergy_CDL6848_20161129.084947.txt
Known Issue/s

## Estimation_AntivImplementat (2 (hidden)
Revised Timeline for Avintiv Implementation Details scope of this release is available at: https://svn.deerwalk.com/projects/usi/roadmap
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import and Analysis - Eligibility and Pharmacy | 2016-08-01 | 1 | 2016-08-01 | Subhad/Sudeep | Not Started
| DSD preparation - Eligibility and Pharmacy | 2016-08-02 | 2 | 2016-08-03 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Eligibility and Pharmacy | 2016-08-04 | 2 | 2016-08-05 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Eligibility and Pharmacy | 2016-08-06 | 1 | 2016-08-06 | Rebika | Not Started
| File Import and Analysis - Medical | 2016-08-09 | 1 | 2016-08-09 | Subhad/Sudeep | Not Started
| DSD preparation - Medical | 2016-08-10 | 2 | 2016-01-01 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Medical | 2016-08-12 | 1 | 2016-08-12 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Medical | 2016-08-15 | 1 | 2016-08-15 | Rebika | Not Started
SPT
| DSD Implementation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 6 | 2016-08-08 | Binod/Rasa | Not Started
| Scrub Engine Configuration |  | 1
| Unit Testing | 2016-08-09 | 2 | 2016-08-10 | Binod/Rasa | Not Started
QA
| Test Data Preparation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 4 | 2016-08-04 | Surya | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-08-11 | 1 | 2016-08-11 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2016-08-12 | 1 | 2016-08-12 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2016-08-15 | 3 | 2016-08-17 | Surya | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-08-17 | 2 | 2016-08-18 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-19 | 1 | 2016-08-19 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-22 | 2 | 2016-08-23 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started | If any
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started | If any
| App Processing | 2016-08-26 | 1 | 2016-08-26 | Processing | Not Started |  | 2016-01-14
| App QC | 2016-08-29 | 1 | 2016-08-29 | Raghu | Not Started |  | 2016-01-14
| Production Release | 2016-08-30 | 1 | 2016-08-30 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Ethos_HistoricalRx_Impl
Timeline for Traffk - Ethos - Historical RX Details scope of this release is available at: https://svn.deerwalk.com/versions/2588
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import, Layout verification and analysis | 2016-12-01 | 1 | 2016-12-01 | Subhad | Completed
| IQR Preparartion and review | 2016-12-02 | 1 | 2016-12-02 | Subhad/Rebika | Completed
SPT
| Issue fixes (109113 - Duplicate values in Unit LOA) | 2016-12-02 | 1 | 2016-12-02 | Binod/Rajesh | Completed
| Issue fixes (108824 - Book of Business inconsistency with comparison data to group) | 2016-12-02 | 1 | 2016-12-02 | Binod/Rajesh | Completed
| Issue fixes (108827 - Unknown group in Pharmacy and LAB data list page) | 2016-12-02 | 1 | 2016-12-02 | Binod/Rajesh | Completed
| Unit Testing | 2016-12-02 | 1 | 2016-12-02 | Binod/Rajesh | Completed | If any
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-12-05 | 1 | 2016-12-05 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2016-12-05 | 1 | 2016-12-05 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2016-12-06 | 1 | 2016-12-06 | Shishir/Akesh | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-12-06 | 1 | 2016-12-06 | Subhad/Binod | Not Started | If any
| Re- scrub | 2016-12-07 | 1 | 2016-12-07 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-12-07 | 1 | 2016-12-07 | Shishir/Akesh | Not Started
| App Processing | 2016-12-08 | 1 | 2016-12-08 | Processing | Not Started |  | 2016-01-14
| App QC | 2016-12-08 | 1 | 2016-12-08 | Raghu | Not Started |  | 2016-01-14
| Production Release | 2016-12-09 | 1 | 2016-12-09 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Holidays
Holidays