## Info
ASUMPTIONS AND DEPENDENCIES
Files listed below are only used during this implementation release. Any addition of the files will change the timeline.
Account structure/s should be available is a day or two.
This implementation will go through scrub engine
New URL for this group is yet to be confirmed.
Request Received for Implementation on 3/08/2017
File received Dates: 20170201, 20170301
Fiest set of files
incoming-das-scrub/traffk/20170201/TopCon/TopconHealthcomp/
J40_TOPCON_HEALTHCOMP_CLAIMS.txt
incoming-das-scrub/traffk/20170301/TopCon/TopconHealthcomp/
Topcon_HealthComp_Eligibility.txt
ProviderTypesCodes.txt
traffk/20161108/uhaul/bradm@uhaul.com/
Uhaul_Traffk_20161008.csv
J40_TOPCON_HEALTHCOMP_CLAIMS.txt
DeniedReasonCodes.txt
BenefitCodes.txt
Known Issue/s

## TopCon_Implementation
Timeline for Traffk - TopCon HealthComp Implementation Details scope of this release is available at: https://deermine.deerwalk.com/versions/3284
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| Generic DSD Preparation (Eligibility and Medical) | 2017-03-09 | 1 | 2017-03-09 | Subhad | Completed
| File Import, Layout verification and analysis for Eligibility and Medical | 2017-03-08 | 1 | 2017-03-08 | Subhad | Completed
| Client specific changes in DSD for Eligibility and Medical | 2017-03-09 | 1 | 2017-03-09 | Subhad | Not Started | Waiting for LOA structure and other client specific changes
| DSD Review and Sign-off for Eligibility and Medical | 2017-03-14 | 1 | 2017-03-14 | Rebika/Subhad | Not Started | Waitinf for DSD feedback/sign-off on 3/13/2017
| File Import, Layout verification and analysis for Pharmacy | 2017-03-14 | 1 | 2017-03-14 | Subhad | Not Started
| Generic DSD Preparation for Pharmacy | 2017-03-14 | 1 | 2017-03-14 | Subhad | Not Started
| Client specific changes in DSD for Pharmacy | 2017-03-15 | 1 | 2017-03-15 | Subhad | Not Started | Waiting for LOA structure and other client specific changes
| DSD Review and Sign-off for Pharmacy | 2017-03-15 | 1 | 2017-03-15 | Rebika/Subhad | Not Started
SPT
| Generic SPT File mapping (Eligibility and Medical) | 2017-03-15 | 3 | 2017-03-17 | Binod/Rajesh | Not Started
| Client specifica DSD Implementation for Eligibility and Medical | 2017-03-15 | 1 | 2017-03-15 | Binod/Rajesh | Not Started
| Client specifica DSD Implementation for Pharmacy | 2017-03-16 | 1 | 2017-03-16 | Binod/Rajesh | Not Started
| Unit Testing for Eligibility and Medical | 2017-03-17 | 1 | 2017-03-17 | Binod/Rajesh | Not Started
| Scrub Engine Configuration | 2017-03-20 | 1 | 2017-03-20 | Binod/Rajesh | Not Started
QA
| Test Data Preparation (Eligbilility, Medical and Pharmacy) | 2017-03-16 | 2 | 2017-03-17 | Shishir/Akesh | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2017-03-20 | 1 | 2017-03-20 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2017-03-21 | 1 | 2017-03-21 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2017-03-22 | 4 | 2017-03-28 | Shishir/Akesh | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2017-03-28 | 2 | 2017-03-29 | Subhad/Binod | Not Started
| Re- scrub | 2017-03-30 | 1 | 2017-03-30 | Processing | Not Started
| Re-scrub QC and Sign-off | 2017-03-31 | 2 | 2017-04-03 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2017-04-04 | 1 | 2017-04-04 | Subhad/Binod | Not Started
| Re- scrub | 2017-04-04 | 1 | 2017-04-04 | Processing | Not Started
| Re-scrub QC and Sign-off | 2017-04-05 | 1 | 2017-04-05 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2017-04-06 | 1 | 2017-04-06 | Subhad/Binod | Not Started | If any
| Re- scrub | 2017-04-06 | 1 | 2017-04-06 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2017-04-07 | 1 | 2017-04-07 | Shishir/Akesh | Not Started | If any
| App Processing | 2017-04-10 | 1 | 2017-04-10 | Processing | Not Started |  | 2016-01-14
| App QC | 2017-04-11 | 1 | 2017-04-11 | Raghu | Not Started |  | 2016-01-14
| Issue fixes for App | 2017-04-12 | 1 | 2017-04-12 | Subhad/Binod/Biswas | Not Started | If any
| Re-App Processing | 2017-04-13 | 1 | 2017-04-13 | Processing | Not Started | If any
| App QC | 2017-04-17 | 1 | 2017-04-17 | Raghu | Not Started | If any
| Production Release | 2017-04-18 | 1 | 2017-04-18 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Estimation_AntivImplementat (2 (hidden)
Revised Timeline for Avintiv Implementation Details scope of this release is available at: https://svn.deerwalk.com/projects/usi/roadmap
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import and Analysis - Eligibility and Pharmacy | 2016-08-01 | 1 | 2016-08-01 | Subhad/Sudeep | Not Started
| DSD preparation - Eligibility and Pharmacy | 2016-08-02 | 2 | 2016-08-03 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Eligibility and Pharmacy | 2016-08-04 | 2 | 2016-08-05 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Eligibility and Pharmacy | 2016-08-06 | 1 | 2016-08-06 | Rebika | Not Started
| File Import and Analysis - Medical | 2016-08-09 | 1 | 2016-08-09 | Subhad/Sudeep | Not Started
| DSD preparation - Medical | 2016-08-10 | 2 | 2016-01-01 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Medical | 2016-08-12 | 1 | 2016-08-12 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Medical | 2016-08-15 | 1 | 2016-08-15 | Rebika | Not Started
SPT
| DSD Implementation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 6 | 2016-08-08 | Binod/Rasa | Not Started
| Scrub Engine Configuration |  | 1
| Unit Testing | 2016-08-09 | 2 | 2016-08-10 | Binod/Rasa | Not Started
QA
| Test Data Preparation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 4 | 2016-08-04 | Surya | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-08-11 | 1 | 2016-08-11 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2016-08-12 | 1 | 2016-08-12 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2016-08-15 | 3 | 2016-08-17 | Surya | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-08-17 | 2 | 2016-08-18 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-19 | 1 | 2016-08-19 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-22 | 2 | 2016-08-23 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started | If any
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started | If any
| App Processing | 2016-08-26 | 1 | 2016-08-26 | Processing | Not Started |  | 2016-01-14
| App QC | 2016-08-29 | 1 | 2016-08-29 | Raghu | Not Started |  | 2016-01-14
| Production Release | 2016-08-30 | 1 | 2016-08-30 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Holidays
Holidays
2017-04-14 | Nepali New Year