## Info
ASUMPTIONS AND DEPENDENCIES
Files listed below are only used during this implementation release. Any addition of the files will change the timeline.
Account structure/s will be available is a day or two.
This implementation will go through scrub engine
New URL for this group is yet to be confirmed.
Request Received for Implementation on 12/01/2017
File received Date: 20170112
Fiest set of files
traffk/20170112/TopCon/BlueShieldCA/
BSCA_Topcon_Rx_Dec14-Nov16.txt
BSCA_Topcon_Med_Dec14-Nov16.txt
BSCA_Topcon_Enrol_Jan14-Nov16.txt
traffk/20161108/uhaul/bradm@uhaul.com/
Uhaul_Traffk_20161008.csv
Known Issue/s

## TopCon_Implementation
Timeline for Traffk - TopCon Implementation Details scope of this release is available at: https://deermine.deerwalk.com/versions/3080
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import, Layout verification and analysis | 2017-01-12 | 2 | 2017-01-13 | Subhad | Ongoing
| DA Checklist preparation (Eligbilility, Medical and Pharmacy) | 2017-01-16 | 2 | 2017-01-17 | Subhad | Not Started
| DSD preparation (Eligbilility, Medical and Pharmacy) | 2017-01-18 | 2 | 2017-01-19 | Subhad | Not Started
| DSD and DA Checklist Review and Sign-off | 2017-01-20 | 1 | 2017-01-20 | Rebika/Subhad | Not Started
SPT
| DSD Implementation (Eligbilility, Medical and Pharmacy) | 2017-01-23 | 4 | 2017-01-26 | Binod/Rajesh | Not Started
| Scrub Engine Configuration | 2017-01-27 | 1 | 2017-01-27 | Binod/Rajesh | Not Started
| Unit Testing | 2017-01-30 | 2 | 2017-01-31 | Binod/Rajesh | Not Started
QA
| Test Data Preparation (Eligbilility, Medical and Pharmacy) | 2017-01-23 | 3 | 2017-01-25 | Shishir/Akesh | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2017-01-30 | 1 | 2017-01-30 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2017-02-01 | 1 | 2017-02-01 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2017-02-02 | 4 | 2017-02-07 | Shishir/Akesh | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2017-02-08 | 2 | 2017-02-09 | Subhad/Binod | Not Started
| Re- scrub | 2017-02-10 | 1 | 2017-02-10 | Processing | Not Started
| Re-scrub QC and Sign-off | 2017-02-13 | 2 | 2017-02-14 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2017-02-15 | 1 | 2017-02-15 | Subhad/Binod | Not Started
| Re- scrub | 2017-02-15 | 1 | 2017-02-15 | Processing | Not Started
| Re-scrub QC and Sign-off | 2017-02-16 | 1 | 2017-02-16 | Shishir/Akesh | Not Started
| Rework DA and SPT | 2017-02-17 | 1 | 2017-02-17 | Subhad/Binod | Not Started | If any
| Re- scrub | 2017-02-17 | 1 | 2017-02-17 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2017-02-20 | 1 | 2017-02-20 | Shishir/Akesh | Not Started | If any
| App Processing | 2017-02-21 | 1 | 2017-02-21 | Processing | Not Started |  | 2016-01-14
| App QC | 2017-02-22 | 1 | 2017-02-22 | Raghu | Not Started |  | 2016-01-14
| Issue fixes for App | 2017-02-23 | 1 | 2017-02-23 | Subhad/Binod/Biswas | Not Started | If any
| Re-App Processing | 2017-02-27 | 1 | 2017-02-27 | Processing | Not Started | If any
| App QC | 2017-02-28 | 1 | 2017-02-27 | Raghu | Not Started | If any
| Production Release | 2017-03-01 | 1 | 2017-03-01 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Estimation_AntivImplementat (2 (hidden)
Revised Timeline for Avintiv Implementation Details scope of this release is available at: https://svn.deerwalk.com/projects/usi/roadmap
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import and Analysis - Eligibility and Pharmacy | 2016-08-01 | 1 | 2016-08-01 | Subhad/Sudeep | Not Started
| DSD preparation - Eligibility and Pharmacy | 2016-08-02 | 2 | 2016-08-03 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Eligibility and Pharmacy | 2016-08-04 | 2 | 2016-08-05 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Eligibility and Pharmacy | 2016-08-06 | 1 | 2016-08-06 | Rebika | Not Started
| File Import and Analysis - Medical | 2016-08-09 | 1 | 2016-08-09 | Subhad/Sudeep | Not Started
| DSD preparation - Medical | 2016-08-10 | 2 | 2016-01-01 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Medical | 2016-08-12 | 1 | 2016-08-12 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Medical | 2016-08-15 | 1 | 2016-08-15 | Rebika | Not Started
SPT
| DSD Implementation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 6 | 2016-08-08 | Binod/Rasa | Not Started
| Scrub Engine Configuration |  | 1
| Unit Testing | 2016-08-09 | 2 | 2016-08-10 | Binod/Rasa | Not Started
QA
| Test Data Preparation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 4 | 2016-08-04 | Surya | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-08-11 | 1 | 2016-08-11 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2016-08-12 | 1 | 2016-08-12 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2016-08-15 | 3 | 2016-08-17 | Surya | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-08-17 | 2 | 2016-08-18 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-19 | 1 | 2016-08-19 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-22 | 2 | 2016-08-23 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started | If any
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started | If any
| App Processing | 2016-08-26 | 1 | 2016-08-26 | Processing | Not Started |  | 2016-01-14
| App QC | 2016-08-29 | 1 | 2016-08-29 | Raghu | Not Started |  | 2016-01-14
| Production Release | 2016-08-30 | 1 | 2016-08-30 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Holidays
Holidays
2017-02-24 | Maha Shivarati Holiday