## Info
ASUMPTIONS AND DEPENDENCIES
URL will be confirmed by 11/21/2016 NST
Known Issue/s

## TimelieTraffkDemoSitewith_WC
Timeline for Traffk's demo site with Demo data including workers comp Details scope of this release is: https://svn.deerwalk.com/issues/107956
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
| URL Creation | 2016-11-21 | 3 | 2016-11-23 | IT/Jeevan | Not Started | For custom url we have following two options: 1) We login to the traffk.com dns panel and point the dns to our custom url 2) We create the custom url and handover it to client and client updates the url
DA
| File Import and Analysis | 2016-11-21 | 1 | 2016-11-21 | Sagun | Not Started
| Logic Update for Workers Comp Demo Data | 2016-11-21 | 1 | 2016-11-21 | Sagun | Not Started
| Issue fixes | 2016-11-23 | 1 | 2016-11-23 | Sagun | Not Started | If Any
| Issue fixes | 2016-11-25 | 1 | 2016-11-25 | Sagun | Not Started | If Any
QA
| Stage Verification | 2016-11-22 | 1 | 2016-11-22 | Surya | Not Started
| Issue verification | 2016-11-23 | 1 | 2016-11-23 | Surya | Not Started
| Issue verification | 2016-11-25 | 1 | 2016-11-25 | Surya | Not Started | If Any
Data Production
| Dump Generation and Trasfer | 2016-11-23 | 1 | 2016-11-23 | Nabindra | Not Started
| Dump Generation and Trasfer (if there is rework after app qc on 11/25/2016) | 2016-11-25 | 1 | 2016-11-25 | Nabindra | Not Started | If Any
Processing Team
| Application Processing [with sdemo dump] | 2016-11-24 | 1 | 2016-11-24 | Sudan | Not Started | Sdemo Dump with workers comp will be provided to processing team once QA is completed for WC data
| Re-application processing after rework on 11/25/2016 | 2016-11-28 | 1 | 2016-11-28 | Sudan | Not Started
PA QA
| Application QC | 2016-11-25 | 1 | 2016-11-25 | Jeevan | Not Started
| Re-work | 2016-11-25 | 1 | 2016-11-25 | Sagun/Surya/Jeevan/Nabindra | Not Started | if any
| Re- Application QC | 2016-11-28 | 1 | 2016-11-28 | Jeevan | Not Started
| Traffk's demo Site Handover | 2016-11-28 | 1 | 2016-11-28 | Sudeep/Jeevan | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## EffortHours
Resources | FTE
Sagun Sapkota (DA) | 2
2016-11-21 | 1
2016-11-23 | 0.5
2016-11-25 | 0.5
Surya Bahadur Bista (Data QC) | 1.5
2016-11-22 | 0.5
2016-11-23 | 0.5
2016-11-25 | 0.5
Sudan Khadgi(Processing) | 1.25
2016-11-23 | 0.25
2016-11-24 | 0.5
2016-11-28 | 0.5
Sudhir Kumar Maharjan (Cloud IT) | 0.625
2016-11-21 | 0.25
2016-11-22 | 0.25
2016-11-23 | 0.125
Jeevan Timilsina (PA QC) | 1.125
2016-11-23 | 0.125
2016-11-25 | 0.5
2016-11-28 | 0.5
Sudeep Khatiwada (Data PM) | 0.375
2016-11-21 | 0.0625
2016-11-22 | 0.0625
2016-11-23 | 0.0625
2016-11-24 | 0.0625
2016-11-25 | 0.0625
2016-11-28 | 0.0625
Total FTE | 6.875
Net Working Days | 6
Working Hours per Day | 8
Total working hour for Demo Site | 55

## Estimation_AntivImplementat (2 (hidden)
Revised Timeline for Avintiv Implementation Details scope of this release is available at: https://svn.deerwalk.com/projects/usi/roadmap
Team | Tasks | Start Date | Day/s to Complete | Completion Date | Assigned To | Status | Remarks
DA
| File Import and Analysis - Eligibility and Pharmacy | 2016-08-01 | 1 | 2016-08-01 | Subhad/Sudeep | Not Started
| DSD preparation - Eligibility and Pharmacy | 2016-08-02 | 2 | 2016-08-03 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Eligibility and Pharmacy | 2016-08-04 | 2 | 2016-08-05 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Eligibility and Pharmacy | 2016-08-06 | 1 | 2016-08-06 | Rebika | Not Started
| File Import and Analysis - Medical | 2016-08-09 | 1 | 2016-08-09 | Subhad/Sudeep | Not Started
| DSD preparation - Medical | 2016-08-10 | 2 | 2016-01-01 | Subhad/Sudeep | Not Started
| DA Checklist preparation - Medical | 2016-08-12 | 1 | 2016-08-12 | Subhad/Sudeep | Not Started
| DSD and DA Checklist Review and Sign-off - Medical | 2016-08-15 | 1 | 2016-08-15 | Rebika | Not Started
SPT
| DSD Implementation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 6 | 2016-08-08 | Binod/Rasa | Not Started
| Scrub Engine Configuration |  | 1
| Unit Testing | 2016-08-09 | 2 | 2016-08-10 | Binod/Rasa | Not Started
QA
| Test Data Preparation (Eligibility, Medical and Pharmacy) | 2016-08-01 | 4 | 2016-08-04 | Surya | Not Started
Processing Cycle Start
| File Arrangement, IQR Processing, IQR QC and Sign-off | 2016-08-11 | 1 | 2016-08-11 | Nisha/Processing/Surya | Not Started
| Scrubbing | 2016-08-12 | 1 | 2016-08-12 | Processing | Not Started |  | 2016-01-12
| Scrub QC and Sign-off | 2016-08-15 | 3 | 2016-08-17 | Surya | Not Started |  | 2016-01-13
Data QC | Rework DA and SPT | 2016-08-17 | 2 | 2016-08-18 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-19 | 1 | 2016-08-19 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-22 | 2 | 2016-08-23 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started
| Rework DA and SPT | 2016-08-24 | 1 | 2016-08-24 | Subhad/Sudeep/Binod | Not Started | If any
| Re- scrub | 2016-08-24 | 1 | 2016-08-24 | Processing | Not Started | If any
| Re-scrub QC and Sign-off | 2016-08-25 | 1 | 2016-08-25 | Surya | Not Started | If any
| App Processing | 2016-08-26 | 1 | 2016-08-26 | Processing | Not Started |  | 2016-01-14
| App QC | 2016-08-29 | 1 | 2016-08-29 | Raghu | Not Started |  | 2016-01-14
| Production Release | 2016-08-30 | 1 | 2016-08-30 | Raghu | Not Started |  | 2016-01-15
Pre-requisite
DA and SPT team need full set of data from CM prior working on these items.

## Holidays
Holidays