## Summary
SUMMARY
Project: | Plan Analytics
Product: | PA
Task/Area/Module/Feature | LOA wise Access and Non-PHI
Makalu Ver: | 6.3.0
Client | Epic
Username | PA_Groupwise
Group | Enervest (PHI) TOPCON ( Non-Phi)
Start Date | End Date | Test Environment | Tester/s | Overall Result | Remarks
2017-05-03 | 2017-05-03 | https://epicbenefitsdata.pa.uat.deerwalk.com | AsmitaS | Pass

## PHI_Non_PHI_Checklist
Test Case ID | Test Area | Sub-section | Test Summary | Expected Result | Test Result
PH01 | Login | Login | 1) Login as a Non-PHI user. | 1) User should be logged in and should be landed to Plan Analytics Dashboard. 2) PHI data(member information) should not be visible to Non PHI users. | Pass
PH02 | Dashboard | Dashboard Charts | 1) Drill down following charts: - Population Risk - Paid Amount PMPM by Relationship - Distribution of Healthfinancial Expenses | 1) PHI information should not be displayed. 2) Drill down from Chronic Conditions Graph should be disabled for groupwise users. | Pass
PH03 | Financial Analytics | Healthplan Snapshot | 1) Click financial Analytics from Report pop down menu. 2) Fill up the FA102 form and Submit. 3) Drill down the value from Summary Page (Healthplan Snapshot) | 1) The popup should contain only the assigned groups and LOAs. 2) PHI information should not be displayed in drilldown. | Pass
PH04 |  | Group Summary | 1) Click on values in # of Subscribers , # of Members, Med Paid, RX paid. | 1) PHI information should not be displayed. | Pass
PH05 |  | HealthCare Trends | 1) Click on Medical. | 1) Drill shouldnot be available in the healthcare trends medical page. | Pass
PH06 |  |  | 1) Click on Pharmacy. | 1) Drill shouldnot be available in the healthcare trends pharmacy page. | Pass
PH07 |  | Network Comparison | 1)Click Network Comparision 2)Drill down #member and #claims | 1) PHI data should not be displayed after drill down. | Pass | no data
PH08 |  | Medical Claim Lag | 1) Click on Medical Claim Lag | 1) Drill down should be disabled. | Pass
PH09 |  | Quality Metric | 1) Click on Quality Metrics page | 1) Drill down should be disabled. | Pass
PH10 |  | Top 20 Reports | 1) Click on Top 20 Diagnosis page. 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH11 |  |  | 1) Click on Top 20 Therpeutic Classes page. 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH12 |  |  | 1) Click on Top 20 Drugs page. 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH13 |  |  | 1) Click on Top 20 Procedure Grouper page 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH14 |  |  | 1)Click on Top 20 Injectable Drugs page 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH15 |  |  | 1)Top 20 Benefit page should appear 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH16 |  |  | 1)Top 20 place of Services page should appear 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH17 |  |  | 1) Top 20 Provider List page should appear 2) Drill down the value | 1) PHI information should not be displayed. | Pass
PH18 |  |  | 1) Top 20 Meg Episodes page should appear 2) Drill down the value | 1) PHI information should not be displayed. | Not Applicable
PH19 |  | Utilization Metrics | 1) Click on Utilization Metrics page 2) Drill down the metrics value | 1) PHI data should not be displayed after drill down. | Pass
PH20 |  | Expense Distribution | 1) Click on Expense Distribution page 2) Drill down the metrics value | 1) PHI data should not be displayed after drill down. | Pass
PH21 |  | High Cost Members | 1) Click on High Cost Members | 1) PHI data should be blinded on High Cost Members page. 2) Exported docs should have the PHI columns removed. | Pass
PH22 |  | Membership Distribution | 1) Click on Membership Distribution page. | 1) PHI data shouldnot be displayed. 2) Drill down should be disabled. | Pass
PH23 |  | Coverage By Relationship | 1) Click on Coverage By Relationship | 1) PHI information should not be displayed. | Pass
PH24 |  | Chronic Conditions | 1) Click on Chronic Conditions | 1) PHI data should not be displayed. 2) Drill down should be disabled. | Pass
PH25 |  | Budget and Fixed Cost | 1) Click on Budget and Fixed Cost | 1) Drill down from the available links. 2) PHI data should not be displayed. | Not Applicable
PH26 |  | Specific Stop Loss | 1) Click on Specific Stop Loss. | 1) Drill down from the available links. 2) PHI data should not be displayed. | Not Applicable
PH27 |  | All | 1) Change reporting period to less than 12 months at financial Analytics popup | 1) Links should be disabled for all the modules in financialAnalytics. 2) High cost member Tab should not be visible. | Pass
PH28 |  |  | 1) Check for Non_PHI Group wise user. | 1) Links in Quality metrics, Healthcare trend, Claim lag and Membership distribution and Chronic Conditions should be disabled. | Pass
PH29 |  | Generate HealthPlan Report | 1)Click HealthPlan Report | 1) PHI data should not be displayed in the report. | Pass
PH30 |  | Generate Custom Report | 1) Click Generate Custom Report | 1) PHI data should not be displayed in the report. 2) The shared report package of other users should not be visible in Load Report Package popup for groupwise users. | Pass
PH31 | Clinical Analytics | Selected Procedure Report | 1)Click on 'Selected Procedure Report' page 2)Drill down the procedure and member count | 1) PHI information should not be displayed. | Pass
PH32 |  | Program Summary | 1)Click on Program Summary (if participation criteria is selected) 2)Drill down Group 3)Drill down any link | 1) PHI information should not be displayed after drilldown | Not Applicable
PH33 |  | Readmission Report | 1) Click on Readmission Report | 1) PHI data should not be displayed. | Pass
PH34 |  | Recent ER Visit | 1) Click on Recent ER Visit Report | 1) PHI data should not be displayed. | Pass
PH35 |  | Potentially Avoidable ER Visits>>By Diagnosis | 1) Click on Potentially Avoidable ER Visits>>By Diagnosis | 1) PHI information should not be displayed after drilldown | Pass
PH36 |  | Potentially Avoidable ER Visits>>By Day of the Week | 1) Click on Potentially Avoidable ER Visits>>By Day of the Week | 1) PHI information should not be displayed after drilldown | Pass
PH37 |  | Generate HealthPlan Report | 1) Click HealthPlan Report | 1) PHI data should not be displayed in the report. | Pass
PH38 |  | Generate Custom Report | 1) Click Generate Custom Report | 1) PHI data should not be displayed in the report. 2) The shared report package of other users should not be visible in Load Report Package popup for groupwise users. | Pass
PH39 | Search | Medical | 1) Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. 2) Modify Criteria should be disabled for PHI data columns. | Pass
PH40 |  |  | 1) Click SumIt and check report. 2) Click Export Report. 3) Click View Member button. | 1) Report Summarized by any category shouldn't display PHI data. 2) Exported Report shouldnot contain PHI data. 3) View Members Result in Member List page shouldnot display PHI data. | Pass
PH41 |  | Pharmacy | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. 2) Modify Criteria should be disabled for PHI data columns. | Pass
PH42 |  |  | 1) Click SumIt and check report. 2) Click Export Report. 3) Click View Member button. | 1) Report Summarized by any category shouldn't display PHI data. 2) Exported Report shouldnot contain PHI data. 3) View Members Result in Member List page shouldnot display PHI data. | Pass
PH43 |  | Eligibility | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Pass
PH44 |  |  | 1) Click Export Report. 2) Click View Member button. | 1) Exported Report shouldnot contain PHI data. 2) View Members Result in Member List page shouldnot display PHI data. | Pass
PH45 |  | Biometrics | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH46 |  |  | 1) Click Export Report. 2) Click View Member button. | 1) Exported Report shouldnot contain PHI data. 2) View Members Result in Member List page shouldnot display PHI data. | Not Applicable
PH47 |  | HRA | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH48 |  |  | 1) Click Export Report. 2) Click View Member button. | 1) Exported Report should not contain PHI data. 2) View Members Result in Member List page shouldnot display PHI data. | Not Applicable
PH49 |  | Workers Comp | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH50 |  | Vision | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH51 |  |  | 1) Click SumIt and check report. 2) Click Export Report. 3) Click View Member button. | 1) Report Summarized by any category shouldn't display PHI data. 2) Exported Report shouldnot contain PHI data. 3) View Members Result in Member List page shouldnot display PHI data. | Not Applicable
PH52 |  | Dental | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH53 |  |  | 1) Click SumIt and check report. 2) Click Export Report. 3) Click View Member button. | 1) Report Summarized by any category shouldn't display PHI data. 2) Exported Report shouldnot contain PHI data. 3) View Members Result in Member List page shouldnot display PHI data. | Not Applicable
PH54 |  | OSHA | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH55 |  | KYN | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH56 |  | Episodes | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH57 |  | Utilization | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Pass
PH58 |  | Participation | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH59 |  | Lab | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Pass | no data
PH60 |  | Vitals | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH61 |  | Diagnosis EMR | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH62 |  | Procedure EMR | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH63 |  | Prescription EMR | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH64 |  | Appointment EMR | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH65 |  | Visit EMR | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. | Not Applicable
PH66 |  |  | 1)See for filter at PHI fields | 1) Filter option at PHI field should not be present. | Not Applicable
PH67 |  | Member Months | 1)Click on the COG Wheel 2) Show/Hide fields 3) Add PHI fields 4) Click on Submit. | 1) PHI info should not be displayed on search results. 2) Modify Criteria should be disabled for PHI data columns. | Pass
PH68 |  |  | 1) Click SumIt and check report. 2) Click Export Report. 3) Click View Member button. | 1) Report Summarized by any category shouldn't display PHI data. 2) Exported Report shouldnot contain PHI data. 3) View Members Result in Member List page shouldnot display PHI data. | Pass
PH69 |  | Member | 1) Click on Member. 2) Fill up the form and click Submit. | 1) PHI info should not be displayed on search results. | Pass
PH70 |  |  | 1) Drill down the MemberID | 1) PHI data should be blinded on Member Summary and Member Detail page. | Pass
PH71 | Care Quality |  | 1)See for filter at PHI fields | 1) Filter option at PHI field should not be present. | Pass
PH72 | Risk Analysis |  | 1) Click on Risk Analysis page. 2) Click on a group that has $ values 3) Click on Employee Count number | 1) PHI info should not be displayed on result page. | Pass
PH73 | Trending and Comparison | Member Profile | 1)Click 'Comparison' tab 2)Add the group from the population. 3)Drilldown the $ amount and member count | 1) PHI info should not be displayed on result page. | Pass
PH74 |  | Comparison page | 1)Drilldown the comparison page 2)Drill down the $ amount and member count | 1) PHI info should not be displayed on result page. | Pass
PH75 | Cohort | Trending page | 1) Check for Cohorts. | 1) Cohort saved by other users shouldn't be displayed for groupwise and NonPHI users. | Pass

## Group_Wise_Users_Access (hidden)
Test Case ID | Test Area | Sub-section | Test Summary | Expected Result | Test Result | Remarks
GW01 | Login | Login | 1) Login as a Restricted Group user. | 1) User should be logged in and should be landed to Plan Analytics Dashboard. | Not Tested
GW02 | Dashboard | Edit Dashboard Population | 1) Verify the "Edit Dashboard Population" popup and its LOAs. | 1) "Edit Dashboard Population" should contain groups and LOAs assigned to the particular user only. | Not Tested
GW03 |  | Dashboard charts | 1) Verify following charts for Group wise access: - Population Risk - Paid Amount PMPM by Relationship - Distribution of Healthcare Expenses - PMPM Trending – Incurred Basis | 1) Charts should display data only for those groups assigned to the user. 2) Drill down should be disabled from Chronic Conditions Chart. | Not Tested
GW04 | Financial Analytics | Financial Analytics>>FA102 popup | 1) Check the dropdown values of LOA | 1) The LOA dropdown should contain only the groups assigned to the user. | Not Tested
GW05 |  | Summary page | 1) Select one group and go to summary page. | 1) The summary page should show the values of that group only. 2) The report text should show the group name selected. | Not Tested
GW06 |  | Drill down to Data search using $ amounts | 1) Check the amount value. | 1) It should show the amount for this group only, not BOB. | Not Tested
GW07 |  | Drill down to Member search using member/subscriber count | 1) Check the count | 1) Member and subscribers count of the assigned only group should be shown, not BOB. | Not Tested
GW08 |  | Drill down to Data search From # Procedure Done | 1)Check the Procedure | 1)It Should show the procedure for this group only | Not Tested
GW09 |  | Generate HealthPlan Report | 1)Generate HealthPlan Report | 1) The report should contain the values of that particular group only. 2) The report text should show the group name selected. | Not Tested
GW10 |  | Generate Custom Report | 1) Generate Report | 1) The report should contain the values of that particular group only. 2) The report text should show the group name selected. 3) The report package saved by other users should not dispalyed for groupwise users in load report package popup. | Not Tested
GW11 | Clinical Analytics | Selected Procedure Report | 1) Select one group and 2) Go to Selected Procedure Report page. | 1) The Selected Procedure Report page should show the values of that group only, not BOB. 2) The report text should show the group name selected. | Not Tested
GW12 |  | Drill down to Member search using #member with procedure count | 1) Check the count | 1)#member with procedure count of the assigned only group should be shown, not BOB. | Not Tested
GW13 |  | Generate HealthPlan Report | 1)TGenerate HealthPlan Report | 1) The report should contain the values of that particular group only. 2) The report text should show the group name selected. | Not Tested
GW14 |  | Generate Custom Report | 1) Generate Report | 1) The report should contain the values of that particular group only. 2) The report text should show the group name selected. 3) The report package saved by other users should not dispalyed for groupwise users in load report package popup. | Not Tested
GW15 | Program Evaluator | Program Evaluator | 1) Click Program Evaluator from Report pop down menu. 2) Fill up the form and Submit. | 1) The report should contain the values of that particular group only. 2) The report text should show the group name selected. | Not Tested
GW16 |  | Program Evaluator/Heat Map | 1)Drill down age band | 1) Drill down should be disabled from the result page. | Not Tested
GW17 | Report Manager | Report Package | 1) Click on Report Manger link in the reports menu. 2) Report package page should contain all the reports. | 1)Exported report should only contain the data of the assigned groups. | Not Tested
GW18 |  | Report Batch | 1) Check the LOAs in the report batch. | 1) The report batch should only contain the assigned groups. | Not Tested
GW19 | Template Manager | Health Plan Snapshot Data | 1) Check for Health Plan Snapshot Data on selecting LOA>>Group | 1) Exported template should contain records of only excluded groups | Not Tested
GW20 |  | Top 20 Data | 1) Check for Top 20s' data on selecting LOA>>Group | 1) Exported template should contain records of only excluded groups | Not Tested
GW21 |  | Membership Distribution by Age/Gender | 1) Check for Membership Distribution by Age/Gender data on selecting LOA>>Group | 1) Exported template should contain records of only excluded groups | Not Tested
GW22 |  | Population and Period(P100) modal | 1) Select created template manager and run P100 appears 2) click Group dropdown | 1) Dropdown should not contain excluded groups. | Not Tested
GW23 |  | Cohort on Population and Period(P100) modal | 1) Select created template manager and run P100 appears 2) click Cohort | 1) Cohort created by normal user/s should not be visible 2) If Cohort by Group is implemented, then records of only included group/s should appear. | Not Tested
GW24 |  | Edit Template | Restricted user should not be able to view the templates created by normal users | Only Templates created by Production User should be editable | Not Tested
GW25 | Report Redesign by Aspose | Report Redesign by Aspose | 1) Export report from FA, CA, Program Evaluator and Report Manager to word and pdf format. | 1)Report should be exported from FA, CA, Program Evaluator and Report Manager to word and pdf in new format according to given template as per the assigned groups. | Not Tested
GW26 | Care Quality | QR100 Popup | 1) Check the dropdown values of LOA | 1) The LOA dropdown should contain only the groups assigned to the user. | Not Tested
GW27 |  | Care quality result page | 1) Check the result. | 1) The result should show the values of this group only. 2) Group information should display the name of this group only. 3) Drill down should be disabled. | Not Tested
GW28 | Search | Medical search page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW29 |  | Medical result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW30 |  | Pharmacy search page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW31 |  | Pharmacy result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW32 |  | Eligibility search page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW33 |  | Eligibility result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW34 |  | Eligibility result page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW35 |  | Workers Comp result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW36 |  | Vision search page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW37 |  | Vision result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW38 |  | Dental search page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW39 |  | Dental result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW40 |  | OSHA result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW41 |  | KYN result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW42 |  | Episodes result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW43 |  | Utilization result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW44 |  | Participation result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW45 |  | Lab EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested | RHP only
GW46 |  | Vitals result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested | RHP only
GW47 |  | Diagnosis EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested | RHP only
GW48 |  | Procedure EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested | RHP only
GW49 |  | Prescription EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested | RHP only
GW50 |  | Appointment EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested | RHP only
GW51 |  | Visit EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested | RHP only
GW52 |  | Member Months search page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW53 |  | Member Months result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW54 |  | Member search page | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW55 |  | Member result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select group and group name and click ok. | 1) The group filter should show only the groups assigned to this user. | Not Tested
GW56 | Risk Analysis | RA100 | 1) Go to risk analysis moudle with "View by Particiaption" checked. | 1) It should list the groups assigned to this user only. | Not Tested
GW57 |  | RA100 | 1) Go to risk analysis moudle with "View by Particiaption" uchecked. | 1) It should list the groups assigned to this user only. | Not Tested
GW58 |  | RA100 | 1) Send to Excel. | 1) Excel report should only show the groups assigned to this user only | Not Tested
GW59 | Trending and Comparison | TC100 | 1) Check the group dropdown list | 1) This should list only the groups assigned to the user. | Not Tested
GW60 |  | TC100 | 1)Add new group population | 1) The population should only conatin the groups assigned to the users,and by that criteria user will able to add the population of choice. | Not Tested
GW61 | Denying access to the Groups |  | Execute test case ID from GW01 to GW33 | 1) The groups which are not assigned to the user should not display. | Not Tested

## Division_wise_Users_Access (hidden)
Test Case ID | Test Area | Sub-section | Test Summary | Expected Result | Test Result | Remarks
GW01 | Login | Login | 1) Login as a Restricted Division user. | 1) User should be logged in and should be landed to Plan Analytics Dashboard. | Not Tested
GW02 | Dashboard | Edit Dashboard Population | 1) Verify the "Edit Dashboard Population" popup and its LOAs. | 1) "Edit Dashboard Population" should contain Divisions and LOAs assigned to the particular user only. | Not Tested
GW03 |  | Dashboard charts | 1) Verify following charts for Division wise access: - Population Risk - Paid Amount PMPM by Relationship - Distribution of Healthcare Expenses - PMPM Trending – Incurred Basis | 1) Charts should display data only for those Divisions assigned to the user. 2) Drill down should be disabled from Chronic Conditions Chart. | Not Tested
GW04 | Financial Analytics | Financial Analytics>>FA102 popup | 1) Check the dropdown values of LOA | 1) The LOA dropdown should contain only the Divisions assigned to the user. | Not Tested
GW05 |  | Summary page | 1) Select one Division and go to summary page. | 1) The summary page should show the values of that Division only. 2) The report text should show the Division name selected. | Not Tested
GW06 |  | Drill down to Data search using $ amounts | 1) Check the amount value. | 1) It should show the amount for this Division only, not BOB. | Not Tested
GW07 |  | Drill down to Member search using member/subscriber count | 1) Check the count | 1) Member and subscribers count of the assigned only Division should be shown, not BOB. | Not Tested
GW08 |  | Drill down to Data search From # Procedure Done | 1)Check the Procedure | 1)It Should show the procedure for this Division only | Not Tested
GW09 |  | Generate HealthPlan Report | 1)Generate HealthPlan Report | 1) The report should contain the values of that particular Division only. 2) The report text should show the Division name selected. | Not Tested
GW10 |  | Generate Custom Report | 1) Generate Report | 1) The report should contain the values of that particular Division only. 2) The report text should show the Division name selected. 3) The report package saved by other users should not dispalyed for Divisionwise users in load report package popup. | Not Tested
GW11 | Clinical Analytics | Selected Procedure Report | 1) Select one Division and 2) Go to Selected Procedure Report page. | 1) The Selected Procedure Report page should show the values of that Division only, not BOB. 2) The report text should show the Division name selected. | Not Tested
GW12 |  | Drill down to Member search using #member with procedure count | 1) Check the count | 1)#member with procedure count of the assigned only Division should be shown, not BOB. | Not Tested
GW13 |  | Generate HealthPlan Report | 1)TGenerate HealthPlan Report | 1) The report should contain the values of that particular Division only. 2) The report text should show the Division name selected. | Not Tested
GW14 |  | Generate Custom Report | 1) Generate Report | 1) The report should contain the values of that particular Division only. 2) The report text should show the Division name selected. 3) The report package saved by other users should not dispalyed for Divisionwise users in load report package popup. | Not Tested
GW15 | Program Evaluator | Program Evaluator | 1) Click Program Evaluator from Report pop down menu. 2) Fill up the form and Submit. | 1) The report should contain the values of that particular Division only. 2) The report text should show the Division name selected. | Not Tested
GW16 |  | Program Evaluator/Heat Map | 1)Drill down age band | 1) Drill down should be disabled from the result page. | Not Tested
GW17 | Report Manager | Report Package | 1) Click on Report Manger link in the reports menu. 2) Report package page should contain all the reports. | 1)Exported report should only contain the data of the assigned Divisions. | Not Tested
GW18 |  | Report Batch | 1) Check the LOAs in the report batch. | 1) The report batch should only contain the assigned Divisions. | Not Tested
GW19 | Report Redesign by Aspose | Report Redesign by Aspose | 1) Export report from FA, CA, Program Evaluator and Report Manager to word and pdf format. | 1)Report should be exported from FA, CA, Program Evaluator and Report Manager to word and pdf in new format according to given template as per the assigned Divisions. | Not Tested
GW20 | Care Quality | QR100 Popup | 1) Check the dropdown values of LOA | 1) The LOA dropdown should contain only the Divisions assigned to the user. | Not Tested
GW21 |  | Care quality result page | 1) Check the result. | 1) The result should show the values of this Division only. 2) Division information should display the name of this Division only. 3) Drill down should be disabled. | Not Tested
GW22 | Search | Medical search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW23 |  | Medical result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW24 |  | Pharmacy search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW25 |  | Pharmacy result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW26 |  | Eligibility search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW27 |  | Eligibility result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW28 |  | Workers Comp search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW29 |  | Workers Comp result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW30 |  | Vision search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW31 |  | Vision result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW32 |  | Dental search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW33 |  | Dental result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW34 |  | OSHA result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW35 |  | KYN result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW36 |  | Episodes result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW37 |  | Utilization result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW38 |  | Participation result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW39 |  | Lab EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested | RHP only
GW40 |  | Vitals result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested | RHP only
GW41 |  | Diagnosis EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested | RHP only
GW42 |  | Procedure EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested | RHP only
GW43 |  | Prescription EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested | RHP only
GW44 |  | Appointment EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested | RHP only
GW45 |  | Visit EMR result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested | RHP only
GW46 |  | Member Months search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW47 |  | Member Months result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW48 |  | Member search page | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW49 |  | Member result page | 1) Click COG Wheel. 2) Show/Hide fields 3) Select Division and Division name and click ok. | 1) The Division filter should show only the Divisions assigned to this user. | Not Tested
GW50 | Risk Analysis | RA100 | 1) Go to risk analysis moudle with "View by Particiaption" checked. | 1) It should list the Divisions assigned to this user only. | Not Tested
GW51 |  | RA100 | 1) Go to risk analysis moudle with "View by Particiaption" uchecked. | 1) It should list the Divisions assigned to this user only. | Not Tested
GW52 |  | RA100 | 1) Send to Excel. | 1) Excel report should only show the Divisions assigned to this user only | Not Tested
GW53 | Trending and Comparison | TC100 | 1) Check the Division dropdown list | 1) This should list only the Divisions assigned to the user. | Not Tested
GW54 |  | TC100 | 1)Add new Division population | 1) The population should only conatin the Divisions assigned to the users,and by that criteria user will able to add the population of choice. | Not Tested
GW55 | Denying access to the Divisions |  | Execute test case ID from GW01 to GW33 | 1) The Divisions which are not assigned to the user should not display. | Not Tested

## Phi_field
Age
Authorization Number
Case Number
Check Number
Claim Number
Contact Name
Contact Phone
Coverage Type Code
Coverage Type Desc
Covered Days
Date Reported
Death Date
Dental Eff Date
Dental Term Date
Disable Length
DOB
Email
Ethnic Group
Fatality
Fracture Cracked Bone
Gender
Incident Date
Incident Time
Insurance Policy Number
Loss Consciousness
Ltd Eff Date
Ltd Term Date
Marital Status
Medical eff date
Medical term date
Member
Member City
Member County
Member DOB
Member First Name
Member Gender
Member ID
Member Last Name
Member LOB Plan Code
Member Middle Name
Member Name
Member PCP Provider ID
Member Phone
Member Region
Member Region Code
Member SSN
Member State
Member Street Address
Member Street Address 2
Member Zip
Not Return Reason
Other First Aid Treatment
Override Osha Recordable
Override Reason
Paid Date
Part of Shift
Physical Therapy
Pre Existing Treatment
Prepare Phone
Preparer Name
Preparer Same as Contact
Preparer Title
Provided By
Provider First Name
Provider ID
Provider Last Name
Provider Middle Name
Provider Name
Provider NPI
Provider TIN
Query Period
Question Work Relatedness
Race
Reason Loss Consciousness
Returned to Work
Service Date
Sharps Brand Name
Standard Threshold Shift
Std Term Date
Still off Work
Time Reported
Unsafe Condition

## Info
TEST RESULT LEGEND
Pass | All test cases pass
Partially Pass | Only some test cases pass
Fail | All test cases fail
Blocked | Test Blocked due to a reason
Ongoing | Test ongoing
Pending | Test pending
Not Tested | Not Tested due to a reason
Not Applicable | Test not applicable for specific clients